## Project Object
业务人员通过定制化产品零部件的灵活应用（配置BOM并显示毛利表），保障生产配置与订单的一致性。
September 2019 Sit

## Non-Function Request
1 | Organization chart 组织结构图
2 | Non-Function request 非功能性需求
| Number | Description
| 1 | 系统人员数量<100 Number of system user <100
| 2 | 公司员工<500人 Number of employee<500
| 3 | 部署在公有云上提供服务 Provide service on cloud
| 4 | 内网单向提供向云提供数据 There is not internet static IP to internal system
| 5 | 经销商将在未来使用系统 Dealer will join the system in the future
3 | Piorities
| Piority | Explaincaption
| 1 | 项目的核心功能，关系到项目的目标，只针对项目的最重要业务和最基础的业务，如果缺少会导致项目的失败。 Generally,it is the core function related to project objects. They are the most important function and basic function of the project objects. The project will be failed if there is not the function.
| 2 | 项目期望的实现，应对业务的完整性和非关键业务需求，这些需求都是需要最终完成。如果缺少，系统也可以正常关键业务的处理，但是这将影响系统的可用性。 The real requirement of project, but it is not related to the key functions. The system should implement them before ending. Those functions will impact the avaliable of system.
| 3 | 应对项目的预期，这样的预期会大大简化用户操作的便利性，加强系统的自动化能力，更好的迎合用户的个性化需求，以及对现有流程可以进行良好的改善。 The requirements are about the function which will simplize the use operatioin, optimize the process and individaul requirement.
| 4 | 对系统的未来扩展和优化 It is about user's hope. Those requirements will make the system better used. All the existing business process could be complete well if lack of those requirement.
4 | 系统角色列表 System Role
| Role Name | Explaincaption
| Sales | The sales who face customer directly for business
B2C Operator
| Support Manager | Help sales to submit the order to BPM for magager's approval and SAP for producting
| Engining Manager | Fill in the engining cost to the order
| Sales Director | The manager of sales department
| Regional Sales Manager | 直接归属销售总监领导的这些人，他们不会录入订单，只会审核订单。但部分大区经理会同时兼任客户经理职责
| System Administrator | 销售 部门的系统管理员而不是来自IT部门。 The key user in sale department, but not from IT department.
| System User | 所有可以访问系统，并使用各种功能的用户，包含系统中的各个角色。 The one who has permission to use the function provided by system.
| 用户 User | 使用权限使用系统的公司员工. The employee or any external people who will use the system.
| 内网系统 The System | Selling tool system
| External User | 经销商等非公司员工，并且他们不拥有公司的内部邮箱和域账号 Dealer or non-employee who there is not domain account
| Domain User | 拥有公司内部邮箱和 域账号的员工和协助人员
5 | Linked external system
Linked System
BPM
Bestsign
Azure SSO
SAP

## Epic
SN# | Piority | Epic Name | Want to | So That
1 | 1 | Domain User Management | Log in system with mail address and password In LDAP | This system does not need to maintain the user information for example the user dimission.
2 | 4 | External User Management | Log in system with mail address and password which verified in registion | Place a customized order
3 | 3 | Role Management | manage the role and permission of operation
4 | 1 | Order management | List or place orders | Submit the customer's requirement
5 | 1 | Append items in order | Fill in B2C or Engining information | The B2C and Engining operation will fill in corresponding cost
6 | 1 | Submit order for approval | Submit order to BPM, it will be sent to SAP after approval | produce following the business equence
7 | 4 | Special approval order | Submit order to SAP for producing and BPM for approvaling at the same time | save time in BPM approval and make order prodce and order approval at the same time
8 | 2 | Make to stock | Make to stock for dealer or key account or own company | Delivery by current stock
9 | 3 | Bidding Management
10 | 2 | Contract Management
11 | 2 | Mail Notification Management | Sent mail to notificate correspond people
12 | 1 | System Setting
13 | 2 | Report
14 | 4 | Dealer Management
15 | 2 | special delivery

## UserStoryV.3
Category | SN# | Epic# | Piority | Role | Story Name | Want to | So That
Use Management | 101 | 1 | 1 | Domain User | user signin | Log in system with mail address and password In internal LDAP | Identify the user roles in system. Avoiding to maintain the user information.
| 102 | 1 | 2 | Domain User | apply for role change | Be a system user or change the role in system | Use system with a defined role
| 103 | 1 | 2 | system user | Approval the role change apply | Apporve the role change requirement from his/her subordinate | Make the applyer using system
| 104 | 1 | 2 | administrator | Approval the role change apply | Apporve the role change requirement from all employee | Apporve the change if the manager is not able to login system
| 105 | 1 | 2 | administrator | list user | List all the system usesr | Could enable/disable system user
| 106 | 1 | 2 | system user | list the subordinate | Check the order from his/her subordinate
| 107 | 1 | 2 | administrator | Disable User
| 108 | 1 | 2 | administrator | Enable User
| 109 | 1 | 2 | system user | search user
| 110 |  |  | system user | user's profile | Edit user's profile
Role Management | 201 | 3 | 3 | Administrator | List roles
| 202 | 3 | 3 | Administrator | List operation gateway
| 203 | 3 | 3 | Administrator | Mangement the relationship between operation and roles
Mail Notifiation | 301 | 11 | 2 | Apporver | Get role change request
| 302 | 11 | 2 | Applyer | Get result notification of role change
| 303 | 11 | 2 | Sales | Draw up contract notification
| 304 | 11 | 2 | Sales | B2C confirmed
| 305 | 11 | 2 | Sales | B2c rejected
| 306 | 11 | 1 | administrator | Sender setup | Set up the default sender(special account in LDAP) for all notification | notify all user by mail via an unified mail
| 307 | 11 | 1 | User | Html format mail template
| 308 | 11 |  |  | has 48 hours timeout token for
| 309 | 11 | 1 | administrator | passing history check
| 310 | 11 | 2 | B2C | Notified if any order need B2C cost
| 311 | 11 | 2 | Engineer | Notified if any order need engining cost
| 312 | 11 | 2 | Support Manager | Notified if any order was submit to headquater & directly deal or not
| 313 | 11 | 2 | Sales | Notified if any order was submited to BPM
| 314 | 11 | 2 | Support Manager | Notified if the order need support manager
| 315 | 11 | 2 | Sales | Notified if any status change in BPM
| 316 | 11 | 2 | Support Manager | Notified if any status change in BPM
| 317 | 11 | 2 | Support Manager | Notified if any special approval request submitted
| 318 | 11 | 2 | Sales | Notified if any special approval request status is changed
| 319 | 11 | 2 | Support Manager | Notified if any special approval request status is changed
| 320 | 11 | 2 | Support Manager | Notified if any special delivery requesst submitted
| 321 | 11 | 2 | Support Manager | Notified if any contact need to deal
| 322 | 11 | 2 | Sales | Notified if any contact need to deal
| 323 | 11 | 2 | Support Manager | Notified if any contact finished the stamp
| 324 | 11 | 2 | Support Manager | Notified if any contact need to stamp
Order Management | 401 | 4 | 1 | Sales | List orders of own's | Know the status of order which is filed by himself/herself | Able to follow up
| 402 | 4 | 1 | Regional Manager | List order of sales who is in his/her regional | Know the status of the order which was placed by the sales in his/her regional | Able to follow up
| 403 | 4 | 1 | Support Manager | List orders of all submited | Check the order status | Able to follow up
| 404 | 4 | 1 | Sales | Save order | Save the order and wait for submit | The sales is able to go on to edit the order
| 405 | 4 | 1 | Sales | Submit the order to headquarter | place an order | the people in headquarter will deal the order in next step
| 406 | 4 | 3 | Headquater Manager | List all orders | Check the order status | Able to follow up
| 407 | 4 | 1 | administrator | List all orders | Check the detail of order status | Fix issue
| 408 | 4 | 1 | system user | List my history order | Check history | Know own's work
| 409 | 5 | 1 | B2C | Fill in the B2C cost | add B2C cost to order | Caculate total cost of the order
| 410 | 5 | 1 | B2C | List orders need to B2C cost | get which order need B2C | Find the order need B2C cost
| 411 | 5 | 1 | Engineer | Fill in the engineer cost | add the cost about installation | Caculate total cost of the order
| 412 | 5 | 1 | Engineer | List orders need to engining cost | List orders about key account and bidding | Find the order need installation cost
| 413 | 4 | 1 | Support Manager | List orders for support manager approval | List all the order finished by B2C and Engineer (B2C and engineer are not needed) | Find the order need to submit to BPM for approval
| 414 | 6 | 1 | Support Manager | Submit the order to BPM | Submit the order to BPM for approval | The order will be alloed to send to BPM for approvaling
| 415 | 6 | 1 | B2C | reject because of B2C | Fill in fine B2C information | Fill in B2C cost
| 416 | 6 | 1 | Engineer | reject because of Engineer | Fill in fine engineer information | Fill in engineer cost
| 417 | 6 | 1 | Support Manager | reject because of anything | confirm all the information is fine | The headerquater manager able to approve the order
| 418 | 7 | 1 | Support Manager | Make the order to SAP after approved in BPM | Send the order to SAP for producing | No need to wait for BPM approval and Make the order to be produced directly
| 419 |  |  |  | order type | chose an order type according to the defination in SAP | Know what need to be filled in
| 420 | 4 | 2 | Sales | sale type | chose a sale type when fill a order according to the defination in SAP | know it is export、domestic or cool room to caculate the total cost
| 421 | 4 | 2 | Sales | delievery address | Chose the address in contract according to the defination in SAP | Know the address of delievery and caculate the transportation expenses
| 422 | 4 | 2 | Sales | key account choice | Chose the key account in contract of order according to the defination in SAP | Know the customer for contract
| 423 | 4 | 2 | Sales | trsnsportation type | Chose the transportation type according to the defination in SAP | caculate the transportation expenses
| 424 | 4 | 2 | Sales | Headquanter of key account | Chose the headquanter of key account according to the defination in SAP | Got the unified discount from headquanter
| 425 | 4 | 2 | Sales | account level | Chose the account level according to the defination in SAP | Show the customer level in customer information part
| 426 | 4 | 2 | Sales | financial settlement type | Chose the financial settlement type according to the defnination in SAP | caculate the transportation expenses
| 427 | 4 | 2 | Sales | Currency type | Chose the currency type according to the defnination in SAP | Exchange the currency to RMB
| 428 | 4 | 2 | Sales | Business type of item | Chose the business type in item according to the defnination in SAP | know the item cost and caculate the total cost
| 429 | 4 | 2 | Sales | Requirement Plan | Chose the requrement plan in item according to the defnination in SAP | Know the sourc of the item
| 430 | 4 | 1 | Sales | Transfer price | Chose the transfer price in item according to the defnination in SAP | Show it in item and caculate the item cost
| 431 | 4 | 2 | Sales | Commercial terms | Chose the commercial terms when it is about export according to the defnination in SAP | Show the commerical terms in the order
| 432 | 4 | 2 | Sales | Unit of Measurement | Chose the Unit of Measurement for each item according to the defnination in SAP | Showed in the item
| 433 | 4 | 2 | Sales | Retail Price | Show the Retail Price for each item according to the defnination in SAP | Showed in the item
| 434 | 4 | 2 | Sales | freight Charge | Show the freight Charge for each item according to the defnination in SAP | Showed in the item
| 435 | 4 | 1 | Sales | configurable table | setup the configurable table for each item according to the defnination in SAP | setup the materials
| 436 | 4 | 1 | Sales | Color Materials | Show the color information for the Material list for each item according to the defnination in SAP | Setup the materials
| 437 | 4 | 1 | Sales | Spilt deliveriable | Deliver each production to differnet address with different time | match the business requirement
| 438 | 4 | 2 | Sales | customer information | Input the customer information | Need review in BPM
| 439 | 4 | 2 | Sales | contract information | Input contract information | Need review in BPM
| 440 | 4 | 2 | Sales | financial settlement | Input finacle settlement information | Need review in BPM
| 441 | 4 | 1 | Sales | config the materials | Input configurable table information | Need review in BPM
| 442 | 4 | 2 | Sales | Production item list | setup the production item list | Need review in BPM
| 443 | 4 | 2 | Sales | Discount information | Input the discount information | Need review in BPM
| 444 | 4 | 2 | Sales | Upload files | Upload some files about the order | Need review in BPM
| 445 | 4 | 2 | Sales | Gross Margin table | Show Gross Margin table for each order with history version | Anybody need to know the gross margin
| 446 | 4 | 1 | WTW Manager | WTW Gross Margin | Show WTW Gross Margin for each order | Employee in headquarter need to know WTM Gross Margin of each order
| 447 | 7 | 2 | Support Manager | Place special approvaled order | fill a request for a special approvaled order | hope the delievery speed more quick
| 448 | 7 | 2 | Support Manager | Approval the special approvaled order | Approval the special approvaled order and the order will be send to SAP for producing | agree the special approvaled order
| 449 | 4 | 1 | Sales | Order version management | Make a version for the order | Compare the Gross Margin in each change
| 450 | 4 | 2 | system user | Gross Margin table export | Export the Gross Margin table in each history version
| 451 | 4 | 1 | WTW Manager | WTW Gross Margin table export | Export the WTW Gross Margin table in each history version
| 452 | 4 | 2 | Support Manager | Place a bulk stock order | Place a order for own company, dealer and key account. | Make to skock
| 453 | 8 | 1 | system user | Gross Margin earn table | list the earn value between customized and standard | Control the cost of customized production
| 454 | 4 | 1 | system user | Export | Export the Order for read-only | share the order to other employee
| 455 | 4 | 1 | Sales | Dealer choice | Chose the dealer in order according to the defination in SAP
| 456 | 4 | 1 | Sales | Sale price | Show the real price in order | Manager want to know that
| 457 | 4 | 2 | Sales | Item list copy | Make a simulate items list in new order
| 458 | 4 | 2 | Sales | Configurable list copy | Make a simulate configurable list
| 459 | 4 | 1 | Sales | shipment change | Change the shipment info
| 460 | 4 | 2 | Sales | distribute | distribute some items
| 461 | 4 | 2 | Support Manager | Shipment for bulk stock | sale the items in bulk stock
| 462 | 4 | 1 | Sales | Cancle order
| 463 | 4 | 1 | Support Manager | Cancle order approve
| 464 | 4 | 1 | system user | search orders | search order according to the privilleges
| 465 | 4 | 1 | sales | list rejected orders
| 466 | 4 | 1 | Support Manager | list rejected orders
| 467 | 4 | 1 | B2C | list rejected orders
| 468 | 4 | 1 | Engineer | list rejected orders
| 469 | 4 | 1 | system user | list SAP orders
| 470 |  |  | sales | list approved orders
| 471 |  |  | Support Manager | list approved orders
| 472 |  |  | B2C | list approved orders
| 473 |  |  | Engineer | list approved orders
| 473 |  |  | administrator | export user | export all user list to excel
| 474 |  |  | 运费原数据导入
| 475 |  |  | 追加运费
| 476 |  |  | Sales | international trade
Bidding Management | 501 | 9 |  | Sales | create bidding order | fill in the bidding information | tracking the result of bidding
| 502 | 9 |  | Sales | update the bidding information | Modify the information of each bidding | get the newest bidding information
| 503 | 9 |  | Sales | List own bidding order | list own bidding | find own bidding
| 504 | 9 |  | system user | List all bindding order | list all the bidding | find the bidding
| 505 | 9 |  | Sales | update bidding status | update the status of the bidding | anybody kown if the bidding is completed
| 506 | 9 |  | system user | Search the bidding | know the biddinng in a report | Statistic the bidding
| 507 | 9 |  | Sales | place order from bidding order | search the bidding | find the bidding
Contract Management | 601 | 10 |  | sales | Draw up a contract | provide the information about contract | draw up the contract
| 602 | 10 |  | Support Manager | Approval the contract | Approval the contract | Review the contract and sign in the contract
| 603 | 10 |  | Support Manager | mail contract to customer | Pass the digital contract to dealer or key account via mail | Dealer will sign and upload the contract to bestsign
| 604 | 10 |  | sales | contract status check | Check the contract status from BestSign | Check the contract and seal
| 605 | 10 |  | Support Manager | Seal | Seal contract in BestSign | Confirm the contract
| 606 | 10 |  | sales | contract files preview | Search and find the digital contract files | review the digital contract any time
| 607 | 10 |  | sales | Invoice information management | Invoice information management | Provide the invoice information to SAP for customer
| 608 | 10 |  | sales | contract version | list all the version of contract | know the history did not implement
| 609 | 10 |  | Support Manager | reject the draf version | need sale refill the contract | sale can refill the contract
| 610 | 10 |  | sales | modify contract | refill the contract | refill the contracct
System Parameter | 701 | 12 |  | administrator | Rate of standard discount | Update the standard discount rate and enable date | All the new order will have the newest standard discount
| 702 | 12 |  | administrator | rate of pre extraction cost | Update the rate of per-extraction cost and set enable date | All the new order will have the newest pre-extraction rate
| 703 | 12 |  | administrator | Domestic tax rate | Update the domestic tax rate and enable date | All the new domestic order will have the newest tax rate
| 704 | 12 |  | administrator | Foreign tax rate | Update the foreign tax rate and enable date | All the new foreign order will have the newest tax rate
Report | 801 |  |  | system user | Breakdown of Procurement and Sales | have a report to show some staticstics about order | make decision for martket
| 802 |  |  | system user | Customize fields | Customized the fields for Breakdown of Procurement and Sales | different peopleo case about different content
| 803 |  |  | system user | Bidding tracking table | track the bidding | have a report to track bidding

## User Story (hidden)
Category | SN# | Epic# | Piority | Story Name | Role | Want to | So That
Use Management | 1 | 1 | 1 | Sign in via LDAP | Domain User | Log in system with mail address and password In LDAP | This system does not need to maintain the user information for example the user dimission.
| 2 | 2 | 4 | Sign in via registed information | External User | Log in system with mail address and password which verified in registion | Place a customized order
| 3 | 2 | 4 | Sign Up | External User | Sign up as a dealer | Customize requirement of order
| 4 | 1 | 1 | Apply for role change | Domain User | have more role or change role | The application could be approvaled by manager
| 5 | 1 | 1 | Approval the apply for role change | Sales Director | Rivew and chagne the application from domain User for the role change | Control the permission of domain user
| 6 | 1 | 2 | Approval the apply for role change | System Administrator | Get list of role change to Sales Director and approval/reject the apply | Help the director approval and reject the apply
| 7 | 1 | 3 | add domain user directly | System Administrator | Add domain user to system | Add sales director to system
| 8 | 1 | 2 | List system user | System Administrator | List all user and role change history | Review the user role change
| 9 | 1 | 2 | List system user | Sales Director | List all user and role change history | Review the user role change
| 10 | 1 | 3 | Disable user | System Administrator | Enable the user when the user was disabled | Restore the permission of the disabled user
| 11 | 1 | 3 | Enable user | System Administrator | Disable the user in system | The enabled user is not able to using system,but it is able to log in
| 12 | 1 | 1 | mail domain | System Administrator | set up mutiple mail domain name for employee | Identify if the user is employee or external user
|  | 2 | 4
Role Management | 13 | 3 | 3 | List roles | System Administrator | List all the roles | understand the permission of each role
| 14 | 3 | 1 | List operation gateway | System Administrator | List all the operation which is able to be configed | Setup the relationship between role and operation
| 15 | 3 | 3 | Mangement the relationship between operation and roles | System Administrator | Map the role and the operation | Config the permission of the role
Order Management | 16 | 4 | 1 | List orders of own's | Sales | Know the status of order which is filed by himself/herself | Able to follow up
| 17 | 4 | 1 | List order of sales who is in his/her regional | Regional Sales Manager | Know the status of the order which was placed by the sales in his/her regional
| 18 | 4 | 1 | List orders of all submited | Sales Director
| 19 | 4 | 2 | Save the order | Sales | Save the order and wait for submit | The sales is able to go on to edit the order
| 20 | 4 | 1 | Submit the order to headquarter | Sales | Submit the order to headquarter | the people in headquarter will deal the order in next step
| 21 | 5 | 1 | Fill in the B2C cost | B2C Operator | add B2C cost to order | Caculate total cost of the order
| 22 | 5 | 1 | List orders need to B2C cost | B2C Operator | List all the order | Find the order need B2C cost
| 23 | 5 | 1 | Fill in the engineer cost | Engining Manager | add the cost about installation | Caculate total cost of the order
| 24 | 5 | 1 | List orders need to engining cost | Engining Manager | List all the order | Find the order need installation cost
| 25 | 6 | 1 | List orders for approval | Support Operator | List all the order | Find the order need to submit to BPM for approval
| 26 | 6 | 1 | Submit the order to BPM | Support Operator | Submit the order to BPM for approval | The order will be alloed to send to SAP for producinig
| 27 | 7 | 3 | Make the order to SAP after approved in BPM | Support Manager | Send the order to SAP for producing | No need to wait for BPM approval and Make the order to be produced directly
| 28 | 4 | 2 | order type | Sales | chose an order type according to the defination in SAP | Know what need to be filled in
| 29 | 4 | 2 | sale type | Sales | chose a sale type when fill a order according to the defination in SAP | know it is export、domestic or cool room to caculate the total cost
| 30 | 4 | 2 | delievery address | Sales | Chose the address in contract according to the defination in SAP | Know the address of delievery and caculate the transportation expenses
| 31 | 4 | 2 | key account choice | Sales | Chose the key account in contract of order according to the defination in SAP | Know the customer for contract
| 32 | 4 | 2 | trsnsportation type | Sales | Chose the transportation type according to the defination in SAP | caculate the transportation expenses
| 33 | 4 | 2 | Headquanter of key account | Sales | Chose the headquanter of key account according to the defination in SAP | Got the unified discount from headquanter
| 34 | 4 | 2 | account level | Sales | Chose the account level according to the defination in SAP | Show the customer level in customer information part
| 35 | 4 | 2 | financial settlement type | Sales | Chose the financial settlement type according to the defnination in SAP | caculate the transportation expenses
| 36 | 4 | 2 | Currency type | Sales | Chose the currency type according to the defnination in SAP | Exchange the currency to RMB
| 37 | 4 | 2 | Business type of item | Sales | Chose the business type in item according to the defnination in SAP | know the itm cost and caculate the total cost
| 38 | 4 | 2 | Requirement Plan | Sales | Chose the requrement plan in item according to the defnination in SAP | Know the sourc of the item
| 39 | 4 | 2 | Transfer price | Sales | Chose the transfer price in item according to the defnination in SAP | Show it in item and caculate the item cost
| 40 | 4 | 2 | Commercial terms | Sales | Chose the commercial terms when it is about export according to the defnination in SAP | Show the commerical terms in the order
| 41 | 4 | 2 | Unit of Measurement | Sales | Chose the Unit of Measurement for each item according to the defnination in SAP | Showed in the item
| 42 | 4 | 2 | Retail Price | Sales | Show the Retail Price for each item according to the defnination in SAP | Showed in the item
| 43 | 4 | 2 | freight Charge | Sales | Show the freight Charge for each item according to the defnination in SAP | Showed in the item
| 44 | 4 | 1 | configurable table | Sales | setup the configurable table for each item according to the defnination in SAP | setup the materials
| 45 | 4 | 1 | Color Materials | Sales | Show the color information for the Material list for each item according to the defnination in SAP | Setup the materials
| 46 | 4 | 2 | Spilt deliveriable | Sales | Deliver each production to differnet address with different time | match the business requirement
| 47 | 4 | 1 | customer information | Sales | Input the customer information | Need review in BPM
| 49 | 4 | 1 | contract information | Sales | Input contract information | Need review in BPM
| 50 | 4 | 1 | financial settlement | Sales | Input finacle settlement information | Need review in BPM
| 51 | 4 | 1 | config the materials | Sales | Input configurable table information | Need review in BPM
| 52 | 4 | 1 | Production item list | Sales | setup the production item list | Need review in BPM
| 53 | 4 | 1 | Discount information | Sales | Input the discount information | Need review in BPM
| 54 | 4 | 1 | Upload files | Sales | Upload some files about the order | Need review in BPM
| 55 | 4 | 1 | Gross Margin table | System User | Show Gross Margin table for each order with history version | Anybody need to know the gross margin
| 56 | 4 | 1 | WTM Gross Margin | Regional Sales Manager | Show WTW Gross Margin for each order | Employee in headquarter need to know WTM Gross Margin of each order
| 57 | 7 | 3 | Place special approvaled order | Sales | fill a request for a special approvaled order | hope the delievery speed more quick
| 58 | 7 | 3 | Approval the special approvaled order | Support Manager | Approval the special approvaled order and the order will be send to SAP for producing | agree the special approvaled order
| 59 | 4 | 1 | Order version management | System User | Make a version for the order | Compare the Gross Margin in each change
| 60 | 4 | 2 | Gross Margin table export | System User | Export the Gross Margin table in each history version
| 61 | 4 | 2 | WTW Gross Margin table export | Regional Sales Manager | Export the WTW Gross Margin table in each history version
| 62 | 8 | 2 | Place a stock order | Support Operator | Place a order for own company, dealer and key account. | Make to skock
| 63 | 8 | 1 | Gross Margin earn table | Support Manager | list the earn value between customized and standard | Control the cost of customized production
| 64 | 4 | 2 | Export | System User | Export the Order for read-only | share the order to other employee
| 201 | 4 | 2 | Dealer choice | Sales | Chose the dealer in order according to the defination in SAP
|  |  |  | 调发 |  | 选择备货的产品
配货
备货
备货发货
Bidding Management | 67 | 9 | 3 | record bidding information | Sales | fill in the bidding information | tracking the result of bidding
| 68 | 9 | 3 | update the bidding information | Sales | Modify the information of each bidding | get the newest bidding information
| 69 | 9 | 3 | bidding List | Sales | list all the bidding | find the bidding
| 70 | 9 | 3 | bidding status | Sales | update the status of the bidding | anybody kown if the bidding is completed
| 71 | 9 | 3 | bidding Report | System User | know the biddinng in a report | Statistic the bidding
| 72 | 9 | 3 | Search the bidding | System User | search the bidding | find the bidding
73
Contract Management | 74 | 10 | 2 | Draw up a contract | Sales | provide the information about contract | draw up the contract
| 75 | 10 | 2 | Approval the contract | Support Operator | Approval the contract | Review the contract and sign in the contract
| 76 | 10 | 2 | mail contract | Support Operator | Pass the digital contract to dealer or key account via mail | Dealer will sign and upload the contract to bestsign
| 77 | 10 | 2 | contract status check | Support Operator | Check the contract status from BestSign | Check the contract and seal
| 78 | 10 | 2 | Seal | Support Operator | Seal contract in BestSign | Confirm the contract
| 79 | 10 | 2 | contract files | Support Operator | Search and find the digital contract files | review the digital contract any time
| 80 | 10 | 2 | Invoice information management | Support Operator | Invoice information management | Provide the invoice information to SAP for customer
| 81 | 10 | 2 | 2 level contract | Sales | Sub-contract has the same contract number as prefix 2-bit sequence number as suffix | All the people the contract's relationship
Mail Notification | 82 | 11 | 1 | Sender | System User | Set up the default sender(special account in LDAP) for all notification | notify all user by mail via an unified mail
| 83 | 11 | 1 | Html format mail | System User
| 84 | 11 | 4 | has 48 hours timeout token for | System User
| 85 | 11 | 2 | passing history | System Administrator
| 86 | 11 | 3 | Notified if any order need B2C cost | B2C Operator
| 87 | 11 | 3 | Notified if any order need engining cost | Engining Manager
| 88 | 11 | 3 | Notified if any order was submited to BPM | Sales
| 89 | 11 | 3 | Notified if the order need support manager | Sales
| 90 | 11 | 3 | Notified if any status change in BPM | Sales
| 91 | 11 | 3 | Notified if the application was rejected | Support Operator
| 92 | 11 | 3 | Notified if the application was approvaled | Sales
| 93 | 11 | 3 | Notified if any special approval request submitted | Support Operator
| 94 | 11 | 3 | Notified if any special approval request approvaled by support operator | Sales Director
| 95 | 11 | 3 | Notified if any special delivery requesst submitted | Support Operator
| 96 | 11 | 3 | Notified if any special delivery requesst successfully to BPM | Sales
| 97 | 11 | 3 | Notified if any contact need to deal | Sales
| 98 | 11 | 3 | Notified if any contact finished the sign | Sales
| 99 | 11 | 3 | Notified if any contact need to sign | Support Operator
System Setting | 100 | 12 | 1 | Rate of standard discount | Sales | Update the standard discount rate and enable date | All the new order will have the newest standard discount
| 101 | 12 | 2 | rate of pre extraction cost | Sales | Update the rate of per-extraction cost and set enable date | All the new order will have the newest pre-extraction rate
| 102 | 12 | 2 | Domestic tax rate | Sales | Update the domestic tax rate and enable date | All the new domestic order will have the newest tax rate
| 103 | 12 | 2 | Foreign tax rate | Sales | Update the foreign tax rate and enable date | All the new foreign order will have the newest tax rate
Report | 104 | 13 | 2 | Breakdown of Procurement and Sales | Sales | have a report to show some staticstics about order | make decision for martket
| 105 | 13 | 3 | Customize fields | Sales | Customized the fields for Breakdown of Procurement and Sales | different peopleo case about different content
| 106 | 13 | 3 | Bidding tracking table | Sales | track the bidding | have a report to track bidding
Dealer Management | 107 | 14 | 4 | generate authorized code | Support Manager | Add new dealer and pass mail about authorized code | the dealer can regist in by the authorized code
| 108 | 14 | 4 | using authorized code | External User | Sign up with authorized code | match the dealer information bewteen inputted and regiested
| 109 | 14 | 4 | Place an order | External User | Place an order | Customize requirement of order
| 110 | 14 | 4 | List own Orders | External User | list the order of correspond dealer | find the order

## Sheet1
order | veriion |  | currency_version | parent
seq123 | v1123123 | pushed to sap | v1123123 | v23242 | detail1
seq123 | v23242 | draft
seq234 | v1 | drap | v1 | v1 | detail
seq345 | v1 |  | v1 | v1 | detail1
dea2

## kanban
ToDo | Open | Completed | Verified
US#424: Headquanter of key account
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 大区与中心对应关系(Sales office and sales group)
US#422: key account choice
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 客户主数据(Customer master data)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 付款条件(Payment terms)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 物料主数据(Material master data)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 价格主数据(Price)
US#422: key account choice
Owner：Zhuwei
Description:
Retrieve data from ST DB to Web Page. 客户主数据(Customer master data)
Owner：Wayne
Description:
Retrieve data from ST DB to Web Page. 物料主数据(Material master data)
Owner：Wayne
Description:
Retrieve data from ST DB to Page. 价格主数据(Price)
Owner：Zhuwei
Description:
Retrieve data from SAP and save to ST DB. 销售区域(Sales office& gourp)
US#421: delievery address Owner：Song
Description:
Show the data to place order page. 到货地址(Sales office& gourp)
Owner：Song
Description:
Show the data to place order page. 终端客户性质(industry code)
Owner：Zhuwei
Description:
Retrieve data from SAP and save to ST DB. 终端客户性质选择 dealer only (industry code)
US#422: key account choice Owner：Song
Description:
Showed the data to place order page. 客户主数据(Customer master data)
US#424: Headquanter of key account
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 终端客户性质(industry code)
US Owner：Song
Description:
Show the data to place order page. 到货地址(Bidding Plan)
Owner：Song
Description:
Show the data to place order page. 调研表的保存到浏览缓存(save of order item)
Owner：Song
Description:
Show the data to place order page. 调研表行项目的复制
(copy of order item)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB.
物料分类(Material Class)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB.
特征(Characteristics)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 付款方式
(biding plan)
Owner：Wayne
Description:
DB comments about order 数据库注释(DB document about order)
Owner：Zhuwei
Description:
DB View about the order vision
订单版本查询(order version list and statusv)
Owner：Zhuwei
Description:
push order into SAP in Bayern
向SAP推送订单(push order to SAP)
Bayern的输入结构见SAP订单创建说明书
Owner：Song
Description:
Show the data to place order page. 货币选择(Currency Choice)
只填写元货币，自动计算出RMB
Owner：Song
Description:
Show the data to place order page. 运输方式(Transport type)
Owner：Zhuwei
Description:
Show the data to place order page. 运输方式(Transport type)
Owner：Song
Description:
Show the data to place order page. 收货方式(received type)
Owner：Chunzhao
Description:
Retrieve data from SAP and save to ST DB. 默认特征(default Characteristics)
Owner：Zhuwei
Description:
search from DB View about the order content by sequence number
订单内容查询(order select)
=>AbsOrder
Owner：Wayne
Description:
Retrieve data from ST DB to web page. 默认特征(default Characteristics)
Owner：Zhuwei
Description:
push order into SAP in Bayern
物料在订单上的分类(material group in order item tab)
常量
Owner：Zhuwei
Description:
Retrieve data from SAP and save to ST DB. 物料评估类(material group)
常量
Owner：Song
Description:
Show the data to place order page.
物料选择（material choice）
Owner：Wayne
Description:
Retrieve data from SAP to Page. 配置新BOM(BOM explosion)
Owner：Wayne
Description:
Retrieve data from SAP to Page.
可选项对比 (Configurable item comparison)
Owner：Wayne
Description:
Retrieve data from SAP to Page.
新BOM价格 (optional price,optional transcation price)
Owner：Wayne
Description:
Retrieve data from ST DB to Page.
特征列表 (charactristic configuration)
Owner：zhuwei
Description:
Retrieve data to from st db to order page. 收货方式(received type)
Owner：Song
Description:
Show the data to place order page.
物料价格（material price）
Owner：song
Description:
Show the data to place order page.
特征列表 (charactristic configuration)
Owner：song
Description:
Show the data to place order page.
提交订单 (post order form)
Owner：song
Description:
Show the data to place order page.
毛利率 (order margin)
Owner：Song
Description:
Show data from ST DB to Page.
可选项对比页面 (Configurable item comparison)
Owner：Song
Description:
Show data from ST DB to Page 配置新BOM(BOM explosion)
Owner：Chunzhao
Description:
Retrieve data from SAP and return data back to frye. 新BOM(Bom explosion)
Owner：Zhuwei
Description:
data conversion from db to sap side
向SAP推送订单(push order to SAP)
业务和数据转换
AbsOrder=>SAP Order
Owner：Song
Description:
Show data from ST DB to Page.
毛利率 (Margin)
Owner：Song
Description:
Show data from ST DB to Page.
订单修改/查看 (Order Change)
Owner：Song
Description:
Show data from ST DB to Page.
工程审核 (Engining cost)
Owner：Song
Description:
Show data from ST DB to Page.
B2C审核 (B2C cost)
Owner：Song
Description:
Show data from ST DB to Page.
支持经理审核 (Support manger review)
Owner：Wayne
Description:
Push data from Page to DB.
提交订单 (post order form)
Owner：Chunzhao
Description:
List orders 订单列表(order list)
查看内容时传递参数seqNumber,version code
Owner：Chunzhao
Description:
data verification Session 内容(session)
userId, office code(attached code)
Owner：Chunzhao
Description:
Data verification
1. currency
2. customer
3. inconterm
4.class
Owner：Zhuwei
Description:
Retrieve data from ST DB to Web Page. 获取具体订单详情seqNumber,version code
需要包括order version列表
Owner：Zhuwei
Description:
Log4j
SAP数据获取的Log
回滚log
Owner：Chunzhao
Description:
获取用户权限列表
privillege list in frye project

## Sprints
sprint1 | 22 July~ 2 Aug
SN# | Active | Duration | comments | stakeholder | status | comments
1 | Software Architecture design document | 3 days | Java Architecture | Wayne Wong | Done | Will change it because of the discuss in Thursday
2 | DB design document | 4 days | MySQL | Wayne Wong | Blocked | 60% completed. 15% will be finished when coding. 25%blocked by: 1. SAP interface and data structure 2. LDAP interface and data structure
3 | UI/UE design fine prototype | 4 days | from Bootstrap demon， HTML files | Chunzhao Wong | open | 1.订单录入页面待确认，（调研表，待办，已处理）未完成。 2. 其他页面已与王明龙确认
4 | BPM interface document and program demon | 1 days | Java program demon | Chunzhao Wong | New
5 | Bestgsign interface document and program demon | 3 days | Java program demon | Chunzhao Wong | New
6 | Software structure program demon | 3 days | Java program demon | Wayne Wong | TBD | Changed by new Requirement
7 | LDAP interface document and program demon | 2 days | using Azure Cloud SSO, talked with Mr. zhou | Chunzhao Wong | Blocked | Blocked by issue # 1
8 | Git | 0 days | Personal Git Account and repository as current solution， Internal server is ready. | Wayne Wong | New
9 | MySQL 8 instance | 1 days | install version 8.0.18 in windows | Wayne Wong | TBD | Had installed in Laptop, will install it on this Friday
Resource
| Wayne | 1/day | Full days
| ChunZhao | 1day=0.5FTE | Full days
Sprint 2 | Goal:Ready for dev
# | Active | Duration | comments | stakeholder | status
1 | Git | 0 days | Personal Git Account and repository as current solution | Wayne Wong | Cancel
2 | Software Architecture design document Improve | 0 days | Java Architecture improve because of new requirement | Wayne Wong | Done
3 | Software structure program demon improve | 2 days | Java program demon improve because of new requirement | Wayne Wong | Cancel
4 | UI/UE design fine prototype | 4 days | from Bootstrap demon， HTML files 1.订单录入页面待确认，（调研表，待办，已处理）未完成。 2. 其他页面已与王明龙确认. | Chunzhao Wong | open
5 | department review | 2days | Review UI/UE, business process with sales department | Wayne/Chun Zhao | Cancel
6 | BPM interface document and program demon | 2 days | Java program demon | Chunzhao Wong | Delayed
7 | Bestgsign interface document and program demon | 3 days | Java program demon | Chunzhao Wong | Delayed
8 | SAP interface program demo | 3 days | it connect current version interface, only connect one interface as demo | Wayne Wong | Delayed
9 | Generally Businesses process document | 3 days | Summarize the business process | Wayne Wong | Done
Resource
| Wayne | 1/day
| ChunZhao | 1day=0.5FTE | s
Duration： | Monday~next Tursday
Sprint 3 | Start to code and implement the common functions
No | Active | Duration | User Story | stakeholder | status | comments
1 | improve the software architecture design | 1day |  | Wayne | Done
2 | imporve UI/UE design fine prototype | 2days |  | chunzhao | Done
3 | department review | 2days |  | Chunzhao/Wayne | Canceled
4 | BPM interface document and program demon | 0day |  | Chunzhao/Wayne | Done
5 | Bestgsign interface document and program demon | 0day |  | Chunzhao/Wayne | Done
6 | SAP interface define and document | 23 Aug. |  | Thomas/Haotian Qi | Delayed | defination of Material, configuration, order, (getMaterialCodebyConfigtable: exception about not able to find the material) , fake data,real structure, due date is 23 Aug.
23 | SAP interface test envoriment | 23 Aug. |  | Haotian Qi | Delayed | will provide at 9/15 and provide a schedule about interface providing.
7 | SAP interface Java implement | 3days |  | Wayne | Blocked | Will start from 9/15
8 | List the user story and feature once again | 3days |  | Wayne | Done
9 | log in | 3days | #101:Sign in via registed information | Chunzhao | Done | LDAP login(mail/domain id,password), remove security verify for each request. Role is save in local
10 | role management | 2days | #13:List roles | Li zuosan | Done
11 | role management | 2days | #14:List operation gateway | Li zuosan | Delayed
12 | role management | 4days | #15:Mangement the relationship between operations and roles | Li zuosan | Delayed | P1: present relationship,p 3:adjust the relationship
13 | git maintance | 1day |  | Wayne | Done
14 | DB schema improve | 0day |  | Wayne | Done
15 | Role Change Apply | 2days | #102:apply for role change | ChunZhao | Delayed
16 | Approve the role change application | 2days | #103:Approval the role change apply(administrator) | ChunZhao | Delayed
17 | Approve the role change application | 2days | #104:Approval the role change apply(system user) | ChunZhao | Delayed
18 | list user | 1day | #105:List all the system usesr | Li zuosan | Done
19 | list the subordinate | 1day | #106:Check the order from his/her subordinate | Li zuosan | Canceled
20 | Disable User | 1day |  | Li zuosan | Done
21 | Enable User | 1day |  | Li zuosan | Done
22 | search user | 1day |  | Li zuosan | Done
N1 | SAP interface define and document | 1day | No.6 | Thomas/Wayne | Done
Resource
| Wayne | 1/day=1FTE
| Li zuosan | 1/day=1FTE
| ChunZhao | 1day=0.5FTE
| Monday~next Tursday | 9day/man | each tursday:update status
Sprint 4 | Goal:order input from sap
No | Active | Duration | User Story | stakeholder | status | comments
1 | redirect to unauthorized page without permission | 1day | #101:Sign in via registed information | Wayne | Delayed | interrupted request for steigenberger
2 | File orders according to privilleges | 0.5day | #101:Sign in via registed information | Chun zhao | Done | include the order type listing
3 | show the menu according to the privilleges | 0.5day | #101:Sign in via registed information | Li zuosan | Done
4 | unifined interface for getting operations list of current user | 1day | #101:Sign in via registed information | Li zuosan | Done | DB View and web service
5 | list own's orders | 5days | #401:List orders of own's | Chun zhao | Done
6 | list sales' orders |  | #402:List order of sales who is in his/her regional | Chun zhao | Done
7 | search orders |  | #464:search orders | Chun zhao | Done
8 | find submited orders |  | #403:List orders of all submited | Chun zhao | Done
9 | list orders |  | #406:List all orders | Chun zhao | Done
10 | list orders |  | #407:List all orders | Chun zhao | Done
11 | history order |  | #408:List my history order | Chun zhao | Done
12 | b2c orders |  | #410:List orders need to B2C cost | Chun zhao | Done
13 | engineer orders |  | #412:List orders need to engining cost | Chun zhao | Done
14 | rejected orders |  | #465:list rejected orders | Chun zhao | Done
15 | rejected orders |  | #466:list rejected orders | Chun zhao | Done
16 | rejected orders |  | #467:list rejected orders | Chun zhao | Done
17 | rejected orders |  | #468:list rejected orders | Chun zhao | Done
18 | list SAP orders |  | #469:list SAP orders | Chun zhao | Done
19 | approved orders |  | #470:list approved orders | Chun zhao | Done
20 | approved orders |  | #470:list approved orders | Chun zhao | Done
21 | approved orders |  | #470:list approved orders | Chun zhao | Done
22 | approved orders |  | #470:list approved orders | Chun zhao | Done
23 | common header html | 1day |  | Chun zhao | Done
24 | common menu html | 1day |  | Chun zhao | Done
25 | common footer html | 0day |  | Chun zhao | Done
26 | role management | 2days | #14:List operation gateway | Li zuosan | Done
27 | role management | 0days | #15:Mangement the relationship between operations and roles | Li zuosan | Done
28 | Role Change Apply | 1days | #102:apply for role change | Chun zhao | Done | Have new idea and waiting for more dicision, due day is 8/30
29 | Approve the role change application | 1days | #103:Approval the role change apply(administrator) | Chun zhao | Done | Have new idea and waiting for more dicision, due day is 8/30
30 | Approve the role change application | 0days | #104:Approval the role change apply(system user) | Chun zhao | Done | Have new idea and waiting for more dicision, due day is 8/30
31 | place order | 8days |  | Wayne | cancel
32 | User Profile | 1day |  | Li zuosan | Done
33 | Rate of standard discount | 2days | #701 | Li zuosan | Done
34 | rate of pre extraction cost |  | #702 | Li zuosan | Done
35 | Domestic tax rate |  | #703 | Li zuosan | Done
36 | Foreign tax rate |  | #704 | Li zuosan | Done
37 | mail by template | 2days | #301:pass mail when Get role change request | Li zuosan | Done
38 | sync data from sap | 7 days | Sales area and sales office | Wayne | Done | without interface, documented data structure only
39 |  |  | Sales office and sales group | Wayne | Done
40 |  |  | Customer master data | Wayne | Done
41 |  |  | Industry | Wayne | Done
42 |  |  | Incoterms | Wayne | Done
43 |  |  | Currency and Exchange rate | Wayne | Done
44 |  |  | Material master data | Wayne | Done
45 |  |  | Price | Wayne | Done
46 |  |  | Characteristic | Wayne | Done
47 |  |  | BOM explosion | Wayne | Delayed
48 |  |  | SO Header status | Wayne | cancel
49 |  |  | SO Item status | Wayne | cancel
50 |  |  | Class | Wayne | Done
Resource
| Wayne | 1/day
| Li zuosan | 1/day
| ChunZhao | 1day=0.75FTE
Sprint 5 | Goal: place complete order
No | Active | Duration | User story | stakeholder | status | comments
1 | Kost DB improve | 1day |  | Wayne | Done(3 days)
2 | redirect to unauthorized page without permission | 1day | #101:Sign in via registed information | Wayne | Postponed | interrupte request to steigenberger for authorization
3 | freight charg import | 4day | #474 | Chun zhao | Done
4 | gross margin | 3.5days | #445:Gross Margin table | Li zuosan | Delayed | (6days need)
5 | WTW margin |  | #446:WTW Gross Margin | Li zuosan | Delayed
6 | special order application | 2days | #447：Place special approvaled order | Li zuosan | Done
7 | approval the special order application |  | #448：Approval the special approvaled order | Li zuosan | Done
8 | export | 2days | #450:Gross Margin table export | Chun zhao/li zuosan | Delayed
9 | export |  | #451:WTW Gross Margin table export | Chun zhao/li zuosan | Delayed
10 | list bidding order | 1day | #503:List own bidding order | Chun zhao | Done
11 | list bidding order |  | #504:List all bindding order | Chun zhao | Done
12 | search bidding order |  | #506：Search the bidding | Chun zhao | Done
13 | report | 1day | #803:Bidding tracking table | Li zuosan | Delayed | Bootstrap-table plugin, DB View
14 | report | 1day | #802:Customize fields | Li zuosan | Delayed | Bootstrap-table plugin, DB View
15 | report | 1.5days | #801:Breakdown of Procurement and Sales | Li zuosan | Delayed | Bootstrap-table plugin, DB View
16 | mail | 4days | #301: | Chun zhao | Done
17 | mail |  | #302: | Chun zhao | Done
18 | mail |  | #303: | Chun zhao | Done
19 | mail |  | #304 | Chun zhao | Done
20 | mail |  | #305 | Chun zhao | Done
21 | mail |  | #306 | Chun zhao | Done
22 | mail |  | #307 | Chun zhao | Done
23 | mail |  | #308 | Chun zhao | Done
24 | mail |  | #309 | Chun zhao | Done
25 | mail |  | #310 | Chun zhao | Done
26 | mail |  | #311 | Chun zhao | Done
27 | mail |  | #312 | Chun zhao | Done
28 | mail |  | #313 | Chun zhao | Done
29 | mail |  | #314 | Chun zhao | Done
30 | mail |  | #315 | Chun zhao | Done
31 | mail |  | #316 | Chun zhao | Done
32 | mail |  | #317 | Chun zhao | Done
33 | mail |  | #318 | Chun zhao | Done
34 | mail |  | #319 | Chun zhao | Done
35 | mail |  | #320 | Chun zhao | Done
36 | mail |  | #321 | Chun zhao | Done
37 | mail |  | #322 | Chun zhao | Done
38 | mail |  | #323 | Chun zhao | Done
39 | mail |  | #324 | Chun zhao | Done
40 | save order | 2days | #404: save order | Wayne | Done | Will finished it in future 2 days
41 | Submit order |  | #405: Submit the order to headquarter | Wayne | Done
42 | B2C cost | 1day | #409: Fill in the B2C cost | Wayne | New
43 | engineer cost |  | #411: Fill in the engineer cost | Wayne | New
44 | place order | 8days | #420: sale type | Wayne | Done
45 | place order |  | #421: delievery address | Wayne | New
46 | place order |  | #422: key account choice | Wayne | New
47 | place order |  | #423: trsnsportation type | Wayne | Done
48 | place order |  | #424: Headquanter of key account | Wayne | New
49 | place order |  | #425: account level | Wayne | Done
50 | place order |  | #426: financial settlement type | Wayne | New
51 | place order |  | #427: Currency type | Wayne | Done
52 | place order |  | #428: Business type of item | Wayne | Done
53 | place order |  | #429: Requirement Plan | Wayne | New
54 | place order |  | #430: Transfer price | Wayne | New
55 | place order |  | #431: Commercial terms | Wayne | New
56 | place order |  | #432: Unit of Measurement | Wayne | New
57 | place order |  | #433: Retail Price | Wayne | New
58 | place order |  | #434: freight Charge | Wayne | Open
59 | place order |  | #435: configurable table | Wayne | New
60 | place order |  | #436: Color Materials | Wayne | New
61 | place order |  | #437: Spilt deliveriable | Wayne | New
62 | place order |  | #438: customer information | Wayne | Done
63 | place order |  | #439: contract information | Wayne | Done
64 | place order |  | #440: financial settlement | Wayne | New
65 | place order |  | #441: config the materials | Wayne | New
66 | place order |  | #442: Production item list | Wayne | New
67 | place order |  | #442: Discount information | Wayne | New
68 | place order | 0.5day | #443: Upload files | Chun zhao | New
69 | sync data from sap |  | BOM explosion | Wayne | Postponed | Planed to implement it in next sprint
70 | place order | 0.5day | #476:international trade | Wayne | Done
71 | Code refact | 2days | code review and refactor | Chun zhao | Open
72 | user profile | 0.5 day | tel phone number in profile | Li zuosan | Done
Resource
| Wayne | 1/day
| Li | 1/day
| ChunZhao | 0.75/day
Sprint 6 | Goal: place and push order to sap
No | Active | Duration | User story | stakeholder | status | comments
1 | redirect to unauthorized page without permission |  | #101:Sign in via registed information |  | Postponed | interrupte request to steigenberger for authorization. These will be implemented when have time
2 | export | 2days | #450:Gross Margin table export | Chun zhao | New
3 | export |  | #451:WTW Gross Margin table export | Chun zhao | New
4 | gross margin | 2days | #445:Gross Margin table | Li zuosan | New
5 | WTW margin |  | #446:WTW Gross Margin | Li zuosan | New
6 | report | 1day | #803:Bidding tracking table |  | New
7 | report | 1day | #802:Customize fields |  | New
8 | report | 1day | #801:Breakdown of Procurement and Sales |  | New
9 | B2C cost | 2day | #409: Fill in the B2C cost | Li Song | New
10 | engineer cost |  | #411: Fill in the engineer cost | Li Song | New
11 | place order | 0.5day | #443: Upload files | Chun zhao | New
12 | sync data from sap |  | BOM explosion |  | Postponed
13 | Code refact | 2days | code review and refactor | Chun zhao | Done
14 | get date from sap | 6 days | Sales area and sales office | Chun zhao | New
15 |  |  | Sales office and sales group | Chun zhao | New
16 |  |  | Customer master data | Chun zhao | Done
17 |  |  | Industry | Chun zhao | New
18 |  |  | Incoterms | Chun zhao | Done
19 |  |  | Currency and Exchange rate | Chun zhao | open
20 |  |  | Material master data | Chun zhao | New
21 |  |  | Price | Chun zhao | New
22 |  |  | Characteristic | Chun zhao | New
23 |  |  | Class | Chun zhao | New
24 | get date from db for order | 5days | #421: delievery address | Li zuosan | New
25 |  |  | #422: key account choice | Li zuosan | New
26 |  |  | #424: Headquanter of key account | Li zuosan | New
27 |  |  | #426: financial settlement type | Li zuosan | New
28 |  |  | #440: financial settlement | Li zuosan | New
29 |  |  | #442: Production item list | Li zuosan | New
30 |  |  | #442: Discount information | Li zuosan | New
31 | push order to sap | 10 days | #441: config the materials | Wayne | New
32 |  |  | #429: Requirement Plan | Wayne | New
33 |  |  | #430: Transfer price | Wayne | New
34 |  |  | #431: Commercial terms | Wayne | New
35 |  |  | #432: Unit of Measurement | Wayne | New
36 |  |  | #433: Retail Price | Wayne | New
37 |  |  | #434: freight Charge | Wayne | Open
38 |  |  | #435: configurable table | Wayne | New
39 |  |  | #436: Color Materials | Wayne | New
40 |  |  | #437: Spilt deliveriable | Wayne | New
41 |  | 5days | Deal order page | Li Song | Open
42 |  | 3 days | Loaded data in Deal order page | Wayne | Open
43 | getting data from DB to Oder create data object |  | order creation | Junlei | Open
| Issue | Submit Date | comments | responser | status | Due Date | Solution
1 | Apply Azure Cloud SSO and LDAP | 2019-07-25 |  | zhou shiyu | cancel |  | BPM will provide the organization
2 | MySQL Server Installation in Server | 2019-07-25 | 10.126.80.27 installated. | Wayne | Done
3 | SAP interface and data structure define document | 2019-07-25 |  | Simon | open | 2019-08-16 | Got draf version
4 | order type | 2019-08-01 | document the order type and SAP interface about order | Simon | done | 2019-08-09 | 3 types, they are Dealer,KeyAccount and bulk
5 | current dev SAP interface | 2019-08-01 | Need server ip and define document | Simon | done | 2019-08-12
RiSK
1 | Have not clear solution about retrieving material by item configurable.
2 | The developing progress of Selling Tool and SAP do not match.
2.1 | SAP interface test envoriment

## Milestone
Milestone date | Goal
2019-09-27 | Push order to SAP
2019-11-15 | Pilot
2019-01-01 | go-live

## BPM
No | name | WS Address | input | output | provider | Summary
1 | SendProcess | prod: http://10.126.80.15/UltimusResources/SaleToolService.asmx dev: http://10.126.81.29/UltimusResources/SaleToolService.asmx | order | error code (0,success) | BPM | Submit an order for approval 1.BPM判断订单类型；2.根据单号抽取数据；3.发起新流程或者提交原流程
2 | ChangOrderProcess | prod: http://10.126.80.15/UltimusResources/SaleToolService.asmx dev: http://10.126.81.29/UltimusResources/SaleToolService.asmx | new order, old order code | error code (0,success) | BPM | Submit an changed order for approval 1.判断毛利变化；2.抽取数据；3.发起新流程或者提交原流程
4 | doUpdateState | prod: http://10.126.80.15/UltimusResources/SaleToolService.asmx dev: http://10.126.81.29/UltimusResources/SaleToolService.asmx | order id,status, approvaled result | bool (True: ok; False: need resend) | Selling Tool | result when BMP complete approval 根据BPM的状态更新订单状态

## Bestsign（Contract Management）
SN | name | webservice地址 | http method | Input | output | summary
1 | download contract file | dev: https://api.bestsign.info/api/contracts/download-file prod: https://api.bestsign.cn/api/contracts/download-file | GET | contractId | 文件流
2 | preview the contract file | dev: https://api.bestsign.info/api/contracts/{contractId}/preview prod: https://api.bestsign.cn/api/contracts/{contractId}/preview | POST | contractId，orderIndex,pageNum,dpi,quality | byte[]图片流
3 | Query contract list | dev: https://api.bestsign.info/api/contracts/{contractId} | GET | contractId | Contract details
prod: https://api.bestsign.cn/api/contracts/{contractId}
4 | sign a contract | dev: https://api.bestsign.info/api/contracts/sign | POST | contractIds | totalAmount,successAmount,failureAmount,errorInfos

## LDAP
Need to be define
Decision:
Connect Azure LDAP
Oauth as the approach of SSO

## SAP Interface
Interface list
NO | Interface Description | Comments
1 | Interface1 销售范围可用订单类型(Order type in sales area)
2 | Interface2 销售范围对应大区关系(Sales area and sales group)
3 | Interface3 大区与中心对应关系(Sales group and sales office)
4 | Interface4 客户主数据(Customer master data)
5 | Interface5 供应商主数据(Supplier master data)
6 | Interface6 客户分类（直销或代理）(Customer classification)
7 | Interface7 运输类型（公司运输或自提）(Mode of transport)
8 | Interface8 隶属关系(Industry) - 年采客户获取
9 | Interface9 客户级别(Industry code)
10 | Interface10 业务员主数据(Salesman master data)
11 | Interface11 付款条件(Payment terms)
12 | Interface12 货币及汇率(Currency and Exchange rate)
13 | Interface13 行项目类别(Item category)
14 | Interface14 订单类型与行项目类别对应关系(SO type and Item category)
15 | Interface15 计划行类别(Schedule line category)
16 | Interface16 行项目类别与计划行对应关系(Item category and Schedule line category)
17 | Interface17 物料主数据(Material master data)
18 | Interface18 客户物料主数据(Customer-material master data)
19 | Interface19 价格主数据(Price)
20 | Interface20 特性(Characteristic)
21 | Interface21 BOM展开(BOM explosion)
22 | Interface22 订单抬头状态(SO Header status)
23 | Interface23 订单行项目状态(SO Item status)
24 | Interface27 生产订单信息(Production Order Information)
25 | Interface28 国际贸易条件(Incoterms)
26 | Interface29 类(Class)
27 | Interface31 分期付款类型（Installation payment types）
28 | Interface32 计量单位(unit of measurement)
29 | Interface33 物料类型Material type）
30 | Interface34 客户组(Customer group)
31 | Interface35 附件上传

## Gross Margin
(类型)销售毛利表
(类型)WTW毛利表
(因素)销售类型
导出
导出历史版本的毛利表
历史版本毛利表
| (cloumn)金额 | (cloumn)不含税金额 | (cloumn)成本 | (cloumn)毛利 | (cloumn)毛利率
(Row)整机柜
(Row)分体柜
(Row)机组
(Row)冷凝器
(Row)散件
(Row)冷库
(Row)B2C
(Row)其他项目收费
(Row)可选项
(Row)安装费
(Row)材料费
(Row)电气费
(Row)维保费
(Row)运费
(Row)预提备件费
(Row)不可预估项